Chaophraya Medical Center (CMC)

# Management Review Minutes

GV-REC-001  |  Record  |  Oversight (GV.OV)

About This Sample: This sample shows how Chaophraya Medical Center (CMC), a fictional private hospital group in Thailand, applies the template. CMC operates two hospitals with about 300 beds, 1,200 staff, and an IT team of 25. CMC is designated Critical Information Infrastructure (CII) in the public health sector and processes sensitive health data under the PDPA. All names, systems, vendors, and figures are fictional.

# 1. Document Control

| Document ID | GV-REC-001 |
| --- | --- |
| Title | Management Review Minutes |
| Version | 1.1 |
| Status | Approved |
| Classification | Internal |
| Document Owner | Security Manager |
| Approver | Information Security Steering Committee (ISSC) |
| Effective Date | 24 July 2026 |
| Review Cycle | Each meeting |
| Next Review | 24 July 2027 |

# 2. Document Profile

| Tier | Tier 4: Form, Register, Record, Report, and Template |
| --- | --- |
| Document Type | Record |
| CSF Function | Govern (GV) |
| CSF Category | Oversight (GV.OV) |
| Level | Required |
| Trigger | ISO 27001 |
| Basis | ISO/IEC 27001:2022 Clause 9.3.3 (results of management reviews) |
| ISO/IEC 27002 theme and tags | Organizational (A.5); tags: Governance, Evidence |
| Package | Core |
| Level for CMC | Expected (CMC triggers: PDPA, CII, Computer Crime Act service provider; ISO/IEC 27001 certification targeted for 2027) |

# 3. Revision History

| Version | Date | Description of Change | Prepared By | Approved By |
| --- | --- | --- | --- | --- |
| 1.0 | 23 May 2025 | Initial release under the CMC security program launched in January 2025. | Security Manager | Information Security Steering Committee (ISSC) |
| 1.1 | 24 July 2026 | Updated after the 2026 Management Review (MR-2026-01) to reflect the revised budget and ISSC decisions. | Security Manager | Information Security Steering Committee (ISSC) |

# 4. Part A: Requirement Fields

## 4.1 Purpose

Requirement: State why the document exists and the outcome it supports.

Sample content

These minutes record the inputs, discussion, decisions, and actions of each management review, as evidence required by ISO/IEC 27001:2022 Clause 9.3.3.

## 4.2 Scope

Requirement: Define the units, people, systems, locations, and third parties covered, and state any exclusions.

Sample content

This record is used by the units and roles named in its parent document (GV-PRC-006) and covers the activities that document defines.

## 4.3 Meeting Details

Requirement: Record date, attendees, quorum, and agenda.

Sample content

| Item | Detail |
| --- | --- |
| Meeting | ISSC Management Review MR-2026-01 |
| Date and place | 22 January 2026, CMC Riverside Board Room |
| Chair | CEO |
| Attendees | CIO, CFO, Medical Director, Director of Nursing, Quality and Risk Management Director, DPO, HR Director, Security Manager (secretary); Internal Audit Manager (observer) |
| Quorum met | Yes |

## 4.4 Inputs Reviewed and Decisions

Requirement: Record each mandatory input, the key points, and the decision.

Sample content

| Input (Clause 9.3.2) | Key points | Decision |
| --- | --- | --- |
| Previous actions | 9 of 11 actions from 2025 closed | Carry forward 2 actions (PAM rollout, vendor tiering) |
| Changes in context | CRC Notification 2024 deadlines; HA re-survey 2027 | Add CII matrix (GV-REG-006) to the document pack |
| Performance and audit results | IA-2025-04: 7 findings (2 High: stale HIS accounts, untested restores) | Approve corrective actions; restore tests monthly for HIS |
| Risk assessment and treatment | Top risk R-001 ransomware remains High (score 12) after backup improvements | Fund MSSP from March 2026 |
| Improvement opportunities | Badge tap login requested by physicians | Pilot on two wards in Q2 2026 |

## 4.5 Action Log

Requirement: Record actions with owners and due dates.

Sample content

| Action ID | Action | Owner | Due date | Status |
| --- | --- | --- | --- | --- |
| MR26-01 | Complete privileged access management for HIS and domain administrators | IT Infrastructure Manager | 30 June 2026 | Closed |
| MR26-02 | Onboard MSSP for 24x7 monitoring | Security Manager | 31 March 2026 | Closed |
| MR26-03 | Run monthly HIS restore tests | IT Infrastructure Manager | Monthly from February 2026 | On track |
| MR26-04 | Pilot badge tap login on Wards 5A and 6B | CIO | 30 June 2026 | Closed |

# 5. Part B: Best Practice

Circulate minutes within five working days and track actions in the corrective action register.

## Common Mistakes to Avoid

Minutes record attendance but not decisions, so auditors cannot see management direction.

# 6. Annex: Traceability and Related Documents

| NIST CSF 2.0 Subcategories | GV.OV-01: Risk management strategy outcomes are reviewed to inform and adjust strategy and direction GV.OV-02: Risk management strategy is reviewed and adjusted to ensure coverage of requirements and risks |
| --- | --- |
| ISO/IEC 27001:2022 | Clause 9.3 |
| NIST SP 800-53 Rev. 5 | PM-9 |
| Legal, Regulatory, and Other References | ISO/IEC 27001:2022 Clause 9.3.3 (results of management reviews) |
| Parent Documents | GV-PRC-006: Management Review Procedure |
| Child Documents | None |