## Category Summary
Function | Category | Category name | Current Tier | Target Tier | Tier gap | Feasibility flag | Gaps | Highest score | Highest band | IMPs
Govern | GV.OC | Organizational Context | 1 | 3 | 2 | Yes | 2 | 12 | High | 3
Govern | GV.RM | Risk Management Strategy | 1 | 3 | 2 | Yes | 2 | 16 | High | 3
Govern | GV.RR | Roles, Responsibilities, and Authorities | 1 | 3 | 2 | Yes | 2 | 16 | High | 3
Govern | GV.PO | Policy | 1 | 3 | 2 | Yes | 2 | 16 | High | 2
Govern | GV.OV | Oversight | 1 | 3 | 2 | Yes | 1 | 9 | Medium | 1
Govern | GV.SC | Cybersecurity Supply Chain Risk Management | 1 | 3 | 2 | Yes | 2 | 20 | Critical | 5
Identify | ID.AM | Asset Management | 1 | 3 | 2 | Yes | 2 | 12 | High | 4
Identify | ID.RA | Risk Assessment | 1 | 3 | 2 | Yes | 2 | 20 | Critical | 4
Identify | ID.IM | Improvement | 1 | 3 | 2 | Yes | 1 | 12 | High | 2
Protect | PR.AA | Identity Management, Authentication, and Access Control | 2 | 3 | 1 | No | 2 | 20 | Critical | 9
Protect | PR.AT | Awareness and Training | 2 | 2 | 0 | No | 1 | 6 | Medium | 1
Protect | PR.DS | Data Security | 1 | 3 | 2 | Yes | 2 | 20 | Critical | 6
Protect | PR.PS | Platform Security | 2 | 2 | 0 | No | 2 | 20 | Critical | 5
Protect | PR.IR | Technology Infrastructure Resilience | 2 | 3 | 1 | No | 2 | 20 | Critical | 3
Detect | DE.CM | Continuous Monitoring | 1 | 3 | 2 | Yes | 2 | 20 | Critical | 4
Detect | DE.AE | Adverse Event Analysis | 1 | 3 | 2 | Yes | 2 | 16 | High | 2
Respond | RS.MA | Incident Management | 1 | 3 | 2 | Yes | 2 | 20 | Critical | 4
Respond | RS.AN | Incident Analysis | 1 | 3 | 2 | Yes | 2 | 12 | High | 3
Respond | RS.CO | Incident Response Reporting and Communication | 1 | 3 | 2 | Yes | 2 | 16 | High | 2
Respond | RS.MI | Incident Mitigation | 1 | 2 | 1 | No | 1 | 15 | High | 1
Recover | RC.RP | Incident Recovery Plan Execution | 1 | 3 | 2 | Yes | 2 | 20 | Critical | 4
Recover | RC.CO | Incident Recovery Communication | 1 | 2 | 1 | No | 1 | 9 | Medium | 1
Total | [6 empty] | 39 |  |  | 72

## Notes
CMC Gap Analysis (Simulated)
Purpose | Gap Findings and Improvement Actions for Chaophraya Medical Center (CMC, fictional), grounded in the Interview export. Same content as the six JSON files for Gap-Analysis-Compact.html.
Tiers | Current and Target Tier per Category come from the Interview export and Workshop profile. Edit only if the source changes.
Cells to edit | Blue text is an input: Tiers, Likelihood, Impact, thresholds. Black text is a formula.
Band thresholds (Moderate appetite) | Minimum score
Critical | 20
High | 10
Medium | 5
Low | 1
Scoring | Score = Likelihood (1 to 5) x highest Impact across six areas (1 to 5). The Gap Analysis HTML recalculates after assessor confirmation.
To verify | Current CII and PDPA reporting timelines must be checked against the latest announcements before use in a real procedure.
Not included | Owner, effort, cost, and timing belong to the Roadmap step. Cross-function dependencies are listed in the Depends on column.

## Gap Register
Gap ID | Function | Category | Category name | Basis | Gap title | Gap statement | Consequence | Linked Subcategories | Gap Type | Likelihood (1-5) | Highest Impact (1-5) | Highest impact area | Score | Band
GAP-GV.OC-01 | Govern | GV.OC | Organizational Context | Observed | Legal duties are documented but not maintained or assigned | CMC records some CII and PDPA duties but does not keep the list current or assign owners, so deadlines depend on individuals. | A missed reporting deadline or failed audit brings regulator action against a CII operator and weakens CMC's position after an incident. | GV.OC-03 | Process | 3 | 4 | legal | 12 | High
GAP-GV.OC-02 | Govern | GV.OC | Organizational Context | Observed | Mission, stakeholder needs, and critical dependencies do not guide decisions | Management has not approved which services and dependencies are critical, so recovery and budget priorities rest on opinion. | In an incident, teams argue over what to restore first, and investment goes to systems that matter less than HIS. | GV.OC-01, GV.OC-02, GV.OC-04, GV.OC-05 | Process | 3 | 4 | ops | 12 | High
GAP-GV.RM-01 | Govern | GV.RM | Risk Management Strategy | Observed | No approved risk objectives, risk method, or appetite | Risk decisions follow individual judgment rather than a method management approved, so executives cannot see which risks exceed tolerance. | The CEO funds or declines security work without a view of risk, so large exposures stay open while small ones consume budget. | GV.RM-01, GV.RM-02, GV.RM-06 | Governance | 4 | 4 | fin | 16 | High
GAP-GV.RM-02 | Govern | GV.RM | Risk Management Strategy | Inferred (Medium) | Cyber risk is missing from enterprise risk reporting and strategy | Cybersecurity risk is probably outside enterprise risk reporting, so the board sees it as an IT cost rather than a business risk. | Security budget requests compete without risk evidence, and the board learns of exposure only after an incident. | GV.RM-03, GV.RM-04, GV.RM-05, GV.RM-07 | Governance | 3 | 3 | fin | 9 | Medium
GAP-GV.RR-01 | Govern | GV.RR | Roles, Responsibilities, and Authorities | Observed | No accountable executive or resourced security function | Security duties sit with IT staff beside operations, and the new Security Manager has no written mandate, authority, or budget. | Risky changes proceed without a security decision, and no one can order containment or fund remediation during an incident. | GV.RR-01, GV.RR-03 | Governance | 4 | 4 | ops | 16 | High
GAP-GV.RR-02 | Govern | GV.RR | Roles, Responsibilities, and Authorities | Observed | System ownership and HR practices omit security duties | PACS and Active Directory have no named business owner, and HR practices carry no security duties, so risk on them has no accountable person. | Control changes on PACS and Active Directory stall, and risk acceptances are made without the people who bear the effect. | GV.RR-02, GV.RR-04 | Governance | 3 | 4 | ops | 12 | High
GAP-GV.PO-01 | Govern | GV.PO | Policy | Observed | No approved security policy covers current systems and duties | CMC has only an unsigned 2019 draft policy that staff never received, so no binding rule covers PDPA, CII, or current systems. | Staff and vendors cannot be held to any rule, and an auditor or regulator finds no approved basis for CMC's controls. | GV.PO-01 | Governance | 4 | 3 | ops | 12 | High
GAP-GV.PO-02 | Govern | GV.PO | Policy | Observed | Policy exceptions are accepted without a record or expiry | CMC has no exception process, so control bypasses such as shared administrator accounts continue without an owner, expiry, or visible risk. | Accepted risks pile up unseen, and shared accounts prevent tracing who acted on patient systems after a breach. | GV.PO-02 | Process | 4 | 4 | ops | 16 | High
GAP-GV.OV-01 | Govern | GV.OV | Oversight | Observed | Leadership receives no regular cybersecurity reporting | Executives hear about cybersecurity only after events, so they cannot judge progress or decide on resources. | The CEO cannot tell whether risk is falling, so funding decisions follow the latest incident and not program results. | GV.OV-01, GV.OV-02, GV.OV-03 | Governance | 3 | 3 | fin | 9 | Medium
GAP-GV.SC-01 | Govern | GV.SC | Cybersecurity Supply Chain Risk Management | Observed | Critical vendor contracts carry no security duties or processing agreements | Contracts with critical vendors lack security duties and processing agreements, so CMC cannot require protection of patient data. | A breach at the HIS or PACS vendor reaches patient data with no contract duty to notify CMC or cooperate. | GV.SC-01, GV.SC-03, GV.SC-05, GV.SC-06 | Process | 4 | 5 | data | 20 | Critical
GAP-GV.SC-02 | Govern | GV.SC | Cybersecurity Supply Chain Risk Management | Observed | Vendors reach critical systems through uncontrolled remote tools | Vendors connect through always-on remote tools that CMC does not control, and they take no part in incident planning or exit steps. | An attacker who takes over a vendor session reaches HIS or PACS directly, as in the attack path used against the peer hospital. | GV.SC-02, GV.SC-04, GV.SC-08, GV.SC-09, GV.SC-10 | Process | 4 | 5 | ops | 20 | Critical
GAP-ID.AM-01 | Identify | ID.AM | Asset Management | Observed | Software, cloud, and data-flow inventories are missing | CMC lists hardware and medical devices but not software, cloud services, or data flows, so exposure and breach scope cannot be mapped. | Unlisted software stays unpatched, and after a breach CMC cannot say which patient records left the hospital. | ID.AM-02, ID.AM-03, ID.AM-04, ID.AM-07 | Process | 3 | 4 | legal | 12 | High
GAP-ID.AM-02 | Identify | ID.AM | Asset Management | Observed | Asset ownership, criticality, and disposal are not managed | Assets lack owners and criticality in the inventory, and devices leave CMC without disk sanitization. | Patient data on a returned disk reaches a third party, and unknown devices join the network unnoticed. | ID.AM-01, ID.AM-05, ID.AM-08 | Process | 3 | 3 | ops | 9 | Medium
GAP-ID.RA-01 | Identify | ID.RA | Risk Assessment | Observed | Internal systems are not scanned and the website carries a known weakness | CMC does not scan its internal systems for vulnerabilities, so known flaws stay open until an outsider finds them. | Attackers use a known flaw on the website or an internal server to gain a foothold and move toward HIS. | ID.RA-01, ID.RA-06, ID.RA-07, ID.RA-08 | Technology | 4 | 5 | ops | 20 | Critical
GAP-ID.RA-02 | Identify | ID.RA | Risk Assessment | Inferred (Medium) | Threats and risk responses are not recorded or tracked | CMC likely rates risks without sector threat information, so it has not judged its exposure to the ransomware that hit a peer hospital. | Controls are chosen without a view of the likely attack path, so spending misses the routes attackers actually use. | ID.RA-02, ID.RA-03, ID.RA-05, ID.RA-09, ID.RA-10 | Process | 3 | 4 | ops | 12 | High
GAP-ID.IM-01 | Identify | ID.IM | Improvement | Observed | No exercises or reviews drive improvement | CMC runs no exercises and does not update its plans from operational lessons, so weaknesses are found only in real events. | Weak response plans and repeated findings first appear during a real attack or at the next audit. | ID.IM-01, ID.IM-02, ID.IM-03, ID.IM-04 | Evidence | 3 | 4 | ops | 12 | High
GAP-PR.AA-01 | Protect | PR.AA | Identity Management, Authentication, and Access Control | Observed | Privileged and vendor access relies on passwords alone | CMC controls who holds an account but not how it proves identity, so its most powerful access paths have the weakest protection. | One stolen administrator or vendor password lets ransomware encrypt HIS and Active Directory, which tolerate under four hours of downtime. | PR.AA-03 | Technology | 4 | 5 | ops | 20 | Critical
GAP-PR.AA-02 | Protect | PR.AA | Identity Management, Authentication, and Access Control | Observed | Access is not controlled across the account life cycle | Access rights depend on individuals instead of a governed process, so no one limits, reviews, or removes access consistently. | Former staff or vendors keep access to patient data unnoticed, and a stolen shared account gives wide reach. | PR.AA-01, PR.AA-02, PR.AA-05, PR.AA-06 | Process | 3 | 5 | data | 15 | High
GAP-PR.AT-01 | Protect | PR.AT | Awareness and Training | Observed | Awareness training is not evidenced beyond phishing reporting | Users can report phishing and simulations run, but no record shows an annual program with completion tracking for all staff. | Staff untrained in general tasks click a phishing link, and CMC cannot show an auditor that training took place. | PR.AT-01 | Evidence | 2 | 3 | ops | 6 | Medium
GAP-PR.DS-01 | Protect | PR.DS | Data Security | Observed | Backups of core systems cannot be shown to survive ransomware | Only the PACS backup has an offline or immutable copy, and no restore test has run on HIS, Microsoft 365, or Active Directory. | Ransomware encrypts data and online backups together, so HIS cannot be restored and care continues on paper for an extended period. | PR.DS-11 | Technology | 4 | 5 | ops | 20 | Critical
GAP-PR.DS-02 | Protect | PR.DS | Data Security | Observed | Patient data is not encrypted and test copies hold production data | Protection of patient data depends on the system, so HIS stores and sends records without full encryption and keeps live copies in test. | A stolen disk, laptop, or intercepted connection exposes sensitive health records and triggers PDPA breach notification. | PR.DS-01, PR.DS-02, PR.DS-10 | Technology | 3 | 5 | data | 15 | High
GAP-PR.PS-01 | Protect | PR.PS | Platform Security | Observed | Critical servers and the website run end-of-life or late-patched software | Platform support is not managed against a patch schedule, so end-of-life and late-patched systems stay in service. | Attackers use a known flaw on PACS or an end-of-life host to enter and spread ransomware inside the network. | PR.PS-02 | Technology | 4 | 5 | ops | 20 | Critical
GAP-PR.PS-02 | Protect | PR.PS | Platform Security | Observed | Legacy medical devices have no compensating protection | Devices that cannot be patched receive no isolation or monitoring, so one infected device can reach clinical systems. | One infected medical device spreads inside a flat network, and loss of imaging delays diagnosis and treatment. | PR.PS-03 | Technology | 4 | 5 | safety | 20 | Critical
GAP-PR.IR-01 | Protect | PR.IR | Technology Infrastructure Resilience | Observed | The network is flat around critical systems | HIS and Active Directory share a flat network, so any compromised device can reach the systems that run the hospital. | Ransomware that enters through any workstation or vendor session spreads to HIS and Active Directory within hours. | PR.IR-01 | Technology | 4 | 5 | ops | 20 | Critical
GAP-PR.IR-02 | Protect | PR.IR | Technology Infrastructure Resilience | Observed | Critical systems will not recover within tolerable downtime | Recovery capacity is not matched to downtime tolerance, so HIS and Active Directory cannot return in the time the hospital can bear. | A failure or attack on HIS stops registration, ordering, and medication records beyond the four-hour tolerance. | PR.IR-03, PR.IR-04 | Technology | 3 | 5 | ops | 15 | High
GAP-DE.CM-01 | Detect | DE.CM | Continuous Monitoring | Observed | Network traffic and server logs are not monitored | No one watches network traffic or reads logs on the core systems, although the hospital runs around the clock. | An intruder works for days unseen, and ransomware is noticed only when files are encrypted. | DE.CM-01, DE.CM-09 | Technology | 4 | 5 | ops | 20 | Critical
GAP-DE.CM-02 | Detect | DE.CM | Continuous Monitoring | Observed | Vendor sessions are unlogged and physical monitoring is unconfirmed | CMC records neither vendor remote sessions nor proof that physical alerts are watched, so misuse leaves little trace. | A vendor or insider can copy patient records without detection, and CMC cannot prove what was accessed. | DE.CM-02, DE.CM-06 | Technology | 4 | 4 | legal | 16 | High
GAP-DE.AE-01 | Detect | DE.AE | Adverse Event Analysis | Observed | No one triages alerts or declares incidents | No team is assigned to analyze alerts, and no rule decides when an event becomes an incident. | Response starts late or not at all, and regulator clocks run before CMC declares an incident. | DE.AE-02, DE.AE-06, DE.AE-08 | Process | 4 | 4 | ops | 16 | High
GAP-DE.AE-02 | Detect | DE.AE | Adverse Event Analysis | Inferred (Medium) | Ransomware precursors are not detected or correlated | CMC probably has no rules for early ransomware signs, so the first visible sign is likely encrypted files. | Encryption spreads across servers before anyone reacts, and recovery starts from a full outage. | DE.AE-03, DE.AE-04 | Technology | 3 | 5 | ops | 15 | High
GAP-RS.MA-01 | Respond | RS.MA | Incident Management | Observed | No tested incident response plan or ransomware playbook | Incidents are handled by whoever is available, with no confirmed playbook, no exercise, and no criteria to start recovery. | Decisions in the first hours are improvised during an attack on a hospital that runs around the clock, and reporting duties are missed. | RS.MA-01, RS.MA-05 | Process | 4 | 5 | ops | 20 | Critical
GAP-RS.MA-02 | Respond | RS.MA | Incident Management | Observed | Incident reports are not triaged, categorized, or escalated | Reports reach IT but no steps triage, rate, or escalate them, so serious incidents cannot be told from routine ones. | A reportable event passes as routine, and CMC misses its CII reporting duty. | RS.MA-02, RS.MA-03, RS.MA-04 | Process | 3 | 3 | ops | 9 | Medium
GAP-RS.AN-01 | Respond | RS.AN | Incident Analysis | Observed | Investigation records and evidence are not preserved | CMC has only partial forensic capability and unsynchronized clocks, so evidence is weak and the entry point stays unknown. | Attackers return through the same route after recovery, and CMC cannot support a regulator inquiry. | RS.AN-06, RS.AN-07 | Process | 3 | 4 | ops | 12 | High
GAP-RS.AN-02 | Respond | RS.AN | Incident Analysis | Inferred (Medium) | CMC cannot estimate how much patient data an incident reached | Missing logs and data maps probably prevent CMC from scoping a breach to specific patient records. | CMC cannot complete a PDPA breach assessment, so it notifies too many patients or too late. | RS.AN-03, RS.AN-08 | Technology | 3 | 4 | legal | 12 | High
GAP-RS.CO-01 | Respond | RS.CO | Incident Response Reporting and Communication | Observed | Regulatory reporting duties are not built into procedures | No procedure or owner covers CII incident reporting or PDPA breach notification, so duties depend on memory under pressure. | CMC misses a reporting deadline during an incident and faces regulator action on top of the attack. | RS.CO-02 | Process | 4 | 4 | legal | 16 | High
GAP-RS.CO-02 | Respond | RS.CO | Incident Response Reporting and Communication | Observed | No roles or templates for sharing incident information | No one is assigned to speak to patients, staff, media, or referring hospitals during an incident. | Conflicting statements damage patient trust and invite media speculation. | RS.CO-03 | Process | 3 | 3 | rep | 9 | Medium
GAP-RS.MI-01 | Respond | RS.MI | Incident Mitigation | Observed | Containment ability exists but decision authority does not | The team can isolate hosts, but no playbook or authority says who orders isolation of core systems, even at night. | Delay in disconnecting lets ransomware spread to more systems and lengthens the outage. | RS.MI-01, RS.MI-02 | Governance | 3 | 5 | ops | 15 | High
GAP-RC.RP-01 | Recover | RC.RP | Incident Recovery Plan Execution | Observed | No recovery plan based on agreed recovery objectives | Recovery objectives and restore order are not agreed, so no plan matches what HIS, PACS, and Active Directory need. | Recovery after ransomware is unplanned, so clinical systems return late and in the wrong order. | RC.RP-01, RC.RP-02, RC.RP-04, RC.RP-06 | Process | 4 | 5 | ops | 20 | Critical
GAP-RC.RP-02 | Recover | RC.RP | Incident Recovery Plan Execution | Observed | Backups and restored systems are never verified | No restore has been tested, so CMC does not know whether backups work or how long recovery takes. | Restores fail or bring back infected data, and clinical staff work without a tested manual fallback. | RC.RP-03, RC.RP-05 | Evidence | 4 | 5 | ops | 20 | Critical
GAP-RC.CO-01 | Recover | RC.CO | Incident Recovery Communication | Observed | No process to communicate during recovery | No process or spokesperson informs patients, referring hospitals, and regulators as services return. | Recovery updates are informal and inconsistent, which prolongs loss of trust. | RC.CO-03, RC.CO-04 | Process | 3 | 3 | rep | 9 | Medium

## Improvement Actions
IMP ID | Gap ID | Category | Angle | Action | Gap Type | Systems | Depends on (same Function) | Gap band
IMP-GV.OC-01-01 | GAP-GV.OC-01 | GV.OC | Fix | Add an owner, review date, and deadline to each duty in the register of CII and PDPA requirements | Process |  |  | High
IMP-GV.OC-01-02 | GAP-GV.OC-01 | GV.OC | Prevent | Review the register every year and after each law or regulator change | Process |  |  | High
IMP-GV.OC-02-01 | GAP-GV.OC-02 | GV.OC | Fix | Present the Criticality A list to the CIO and CEO for approval and link it to recovery priorities | Process |  |  | High
IMP-GV.RM-01-01 | GAP-GV.RM-01 | GV.RM | Fix | Approve a risk appetite statement and one risk method | Governance |  |  | High
IMP-GV.RM-01-02 | GAP-GV.RM-01 | GV.RM | Fix | Start a shared risk register that executives review | Governance |  | IMP-GV.RM-01-01 | High
IMP-GV.RM-02-01 | GAP-GV.RM-02 | GV.RM | Prevent | Add cybersecurity risks to the enterprise risk report presented to the board each quarter | Governance |  | IMP-GV.RM-01-01 | Medium
IMP-GV.RR-01-01 | GAP-GV.RR-01 | GV.RR | Fix | Issue a mandate letter for the Security Manager covering authority, reporting line, and budget, and name an accountable executive | Governance |  |  | High
IMP-GV.RR-02-01 | GAP-GV.RR-02 | GV.RR | Fix | Name a business owner for PACS and Active Directory and record the owner duties | Governance | PACS, Active Directory |  | High
IMP-GV.RR-02-02 | GAP-GV.RR-02 | GV.RR | Prevent | Add security duties to job descriptions and joiner, mover, and leaver steps with HR | Governance |  |  | High
IMP-GV.PO-01-01 | GAP-GV.PO-01 | GV.PO | Fix | Approve the Information Security Policy and communicate it to all staff and vendors | Governance |  |  | High
IMP-GV.PO-02-01 | GAP-GV.PO-02 | GV.PO | Handle exceptions | Introduce a policy exception form with risk owner, compensating control, and expiry date | Process |  | IMP-GV.PO-01-01 | High
IMP-GV.OV-01-01 | GAP-GV.OV-01 | GV.OV | Fix | Set up a security steering committee that meets quarterly with a baseline metric set | Governance |  |  | Medium
IMP-GV.SC-01-01 | GAP-GV.SC-01 | GV.SC | Fix | Add security clauses and a data processing agreement to the HIS and PACS vendor contracts | Process | HIS, PACS |  | Critical
IMP-GV.SC-01-02 | GAP-GV.SC-01 | GV.SC | Prevent | Require security due diligence before every new critical vendor contract | Process |  |  | Critical
IMP-GV.SC-02-01 | GAP-GV.SC-02 | GV.SC | Fix | Replace unattended vendor remote tools with a supervised access method protected by MFA | Process | HIS, PACS |  | Critical
IMP-GV.SC-02-02 | GAP-GV.SC-02 | GV.SC | Find | Rank all vendors by criticality and list the access each one holds | Process |  |  | Critical
IMP-GV.SC-02-03 | GAP-GV.SC-02 | GV.SC | Prevent | Include critical vendors in incident response planning and contract exit steps | Process |  |  | Critical
IMP-ID.AM-01-01 | GAP-ID.AM-01 | ID.AM | Find | Build a software and cloud service inventory with version and support status, Criticality A systems first | Process |  |  | High
IMP-ID.AM-01-02 | GAP-ID.AM-01 | ID.AM | Find | Map network and patient data flows for HIS, PACS, LIS, and ERP and start the Record of Processing Activities (ROPA) | Process |  |  | High
IMP-ID.AM-02-01 | GAP-ID.AM-02 | ID.AM | Fix | Assign an owner and criticality to every hardware and medical device record | Process |  |  | Medium
IMP-ID.AM-02-02 | GAP-ID.AM-02 | ID.AM | Prevent | Require inventory update in change approval and reconcile it every six months | Process |  | IMP-ID.AM-02-01 | Medium
IMP-ID.RA-01-01 | GAP-ID.RA-01 | ID.RA | Fix | Run authenticated vulnerability scans monthly on Criticality A systems and the hospital website and track findings to closure | Technology | HIS, PACS, Hospital website |  | Critical
IMP-ID.RA-01-02 | GAP-ID.RA-01 | ID.RA | Prevent | Set remediation timelines by severity and report them to the steering committee | Technology |  | IMP-ID.RA-01-01 | Critical
IMP-ID.RA-02-01 | GAP-ID.RA-02 | ID.RA | Find | Write ransomware and third-party access threat scenarios from the peer hospital incident | Process |  |  | High
IMP-ID.RA-02-02 | GAP-ID.RA-02 | ID.RA | Prevent | Subscribe to a sector threat advisory source and review it monthly | Process |  |  | High
IMP-ID.IM-01-01 | GAP-ID.IM-01 | ID.IM | Find | Run a first tabletop exercise on ransomware and record the improvements | Evidence |  |  | High
IMP-ID.IM-01-02 | GAP-ID.IM-01 | ID.IM | Prevent | Open an improvement register fed by exercises, audits, and incidents | Evidence |  |  | High
IMP-PR.AA-01-01 | GAP-PR.AA-01 | PR.AA | Fix | Enforce MFA for administrators on HIS, PACS, and Active Directory | Technology | HIS, PACS, Active Directory |  | Critical
IMP-PR.AA-01-02 | GAP-PR.AA-01 | PR.AA | Fix | Require MFA and session logging for vendor remote access and remove unattended remote tools | Technology | HIS, PACS |  | Critical
IMP-PR.AA-01-03 | GAP-PR.AA-01 | PR.AA | Find | List every system with its authentication method and MFA status, Criticality A and B first | Technology |  |  | Critical
IMP-PR.AA-01-04 | GAP-PR.AA-01 | PR.AA | Prevent | Approve an authentication standard that requires MFA for new systems | Technology |  |  | Critical
IMP-PR.AA-01-05 | GAP-PR.AA-01 | PR.AA | Handle exceptions | Place systems that cannot support MFA behind a jump host with session logging and a time-limited risk acceptance | Technology |  | IMP-PR.AA-01-04 | Critical
IMP-PR.AA-02-01 | GAP-PR.AA-02 | PR.AA | Fix | Run a first access review on Criticality A systems, privileged accounts first | Process | HIS, PACS, Active Directory |  | High
IMP-PR.AA-02-02 | GAP-PR.AA-02 | PR.AA | Find | Identify shared and generic administrator accounts on PACS, Active Directory, and the website | Process | PACS, Active Directory |  | High
IMP-PR.AA-02-03 | GAP-PR.AA-02 | PR.AA | Prevent | Link joiner, mover, and leaver steps to HR and set a six-month review cycle | Process |  |  | High
IMP-PR.AA-02-04 | GAP-PR.AA-02 | PR.AA | Fix | Keep server room access logs and review the access list each quarter | Process |  |  | High
IMP-PR.AT-01-01 | GAP-PR.AT-01 | PR.AT | Fix | Record completion of an annual awareness program for all staff | Evidence |  |  | Medium
IMP-PR.DS-01-01 | GAP-PR.DS-01 | PR.DS | Fix | Add an offline or immutable backup copy for HIS, ERP, Active Directory, and Microsoft 365 data | Technology | HIS, ERP, Active Directory |  | Critical
IMP-PR.DS-01-02 | GAP-PR.DS-01 | PR.DS | Fix | Run and record a restore test on HIS, Microsoft 365, and Active Directory with recovery time measured | Technology | HIS, Active Directory |  | Critical
IMP-PR.DS-01-03 | GAP-PR.DS-01 | PR.DS | Prevent | Set a restore test schedule for Criticality A systems | Technology |  | IMP-PR.DS-01-02 | Critical
IMP-PR.DS-02-01 | GAP-PR.DS-02 | PR.DS | Fix | Encrypt the HIS database and enforce TLS on all HIS connections | Technology | HIS |  | High
IMP-PR.DS-02-02 | GAP-PR.DS-02 | PR.DS | Fix | Replace production personal data in test with masked data | Technology | HIS |  | High
IMP-PR.DS-02-03 | GAP-PR.DS-02 | PR.DS | Find | Confirm the encryption status of PACS, LIS, and ERP | Technology | PACS, LIS, ERP |  | High
IMP-PR.PS-01-01 | GAP-PR.PS-01 | PR.PS | Fix | Upgrade or isolate the end-of-life PACS platform and the website host | Technology | PACS, Hospital website |  | Critical
IMP-PR.PS-01-02 | GAP-PR.PS-01 | PR.PS | Find | List all systems past end of support with their owners | Technology |  |  | Critical
IMP-PR.PS-01-03 | GAP-PR.PS-01 | PR.PS | Prevent | Set patch timelines by severity and track compliance monthly | Technology |  |  | Critical
IMP-PR.PS-02-01 | GAP-PR.PS-02 | PR.PS | Handle exceptions | Isolate legacy medical devices in a dedicated segment and restrict their traffic | Technology | Legacy medical devices |  | Critical
IMP-PR.PS-02-02 | GAP-PR.PS-02 | PR.PS | Prevent | Add patching and support terms to medical device vendor contracts | Technology |  |  | Critical
IMP-PR.IR-01-01 | GAP-PR.IR-01 | PR.IR | Fix | Segment the network so HIS, PACS, Active Directory, medical devices, and guest Wi-Fi sit in separate zones with filtered access | Technology | HIS, PACS, Active Directory |  | Critical
IMP-PR.IR-02-01 | GAP-PR.IR-02 | PR.IR | Find | Test whether HIS and Active Directory can recover within tolerable downtime | Technology | HIS, Active Directory |  | High
IMP-PR.IR-02-02 | GAP-PR.IR-02 | PR.IR | Fix | Design a failover or recovery option for the HIS database | Technology | HIS |  | High
IMP-DE.CM-01-01 | GAP-DE.CM-01 | DE.CM | Fix | Enable security logs on HIS and PACS and deploy central logging for Criticality A systems | Technology | HIS, PACS |  | Critical
IMP-DE.CM-01-02 | GAP-DE.CM-01 | DE.CM | Prevent | Agree a monitoring model, in-house or managed service, for 24 hour coverage | Technology |  | IMP-DE.CM-01-01 | Critical
IMP-DE.CM-01-03 | GAP-DE.CM-01 | DE.CM | Fix | Install endpoint protection on the PACS servers | Technology | PACS |  | Critical
IMP-DE.CM-02-01 | GAP-DE.CM-02 | DE.CM | Fix | Log vendor remote sessions to HIS and PACS and review the logs weekly | Technology | HIS, PACS |  | High
IMP-DE.AE-01-01 | GAP-DE.AE-01 | DE.AE | Fix | Define alert triage steps and incident declaration criteria | Process |  |  | High
IMP-DE.AE-02-01 | GAP-DE.AE-02 | DE.AE | Prevent | Build detection rules for mass file renames, backup deletion, and new administrator accounts | Technology |  | IMP-DE.CM-01-01 | High
IMP-RS.MA-01-01 | GAP-RS.MA-01 | RS.MA | Fix | Approve an incident response plan with a ransomware playbook | Process |  |  | Critical
IMP-RS.MA-01-02 | GAP-RS.MA-01 | RS.MA | Prevent | Hold a tabletop exercise on ransomware each year | Process |  | IMP-RS.MA-01-01 | Critical
IMP-RS.MA-02-01 | GAP-RS.MA-02 | RS.MA | Fix | Define triage, severity, and escalation steps and start an incident log | Process |  |  | Medium
IMP-RS.MA-02-02 | GAP-RS.MA-02 | RS.MA | Fix | Keep a current contact list and an out-of-band channel for responders | Process |  |  | Medium
IMP-RS.AN-01-01 | GAP-RS.AN-01 | RS.AN | Prevent | Define evidence preservation steps and retain a forensic provider | Process |  |  | High
IMP-RS.AN-01-02 | GAP-RS.AN-01 | RS.AN | Fix | Synchronize system clocks to a trusted time source | Process |  |  | High
IMP-RS.AN-02-01 | GAP-RS.AN-02 | RS.AN | Find | Extend log retention on HIS and PACS to support scoping of affected records | Technology | HIS, PACS |  | High
IMP-RS.CO-01-01 | GAP-RS.CO-01 | RS.CO | Fix | Write a notification procedure with owner, timeline, and template for CII and PDPA reporting after verifying current timelines | Process |  |  | High
IMP-RS.CO-02-01 | GAP-RS.CO-02 | RS.CO | Prevent | Name communication roles and prepare message templates for patients, staff, and media | Process |  |  | Medium
IMP-RS.MI-01-01 | GAP-RS.MI-01 | RS.MI | Fix | Record who may isolate which systems, including a night shift rule for HIS, in the response plan | Governance | HIS |  | High
IMP-RC.RP-01-01 | GAP-RC.RP-01 | RC.RP | Fix | Agree recovery objectives for HIS, PACS, and LIS and write a recovery plan with restore order | Process | HIS, PACS, LIS |  | Critical
IMP-RC.RP-01-02 | GAP-RC.RP-01 | RC.RP | Find | Evaluate a recovery site or cloud recovery option for HIS and Active Directory | Process | HIS, Active Directory |  | Critical
IMP-RC.RP-02-01 | GAP-RC.RP-02 | RC.RP | Prevent | Check backup integrity before every restore and verify restored systems before release | Evidence |  |  | Critical
IMP-RC.RP-02-02 | GAP-RC.RP-02 | RC.RP | Fix | Document paper-based downtime procedures for the wards | Evidence |  |  | Critical
IMP-RC.CO-01-01 | GAP-RC.CO-01 | RC.CO | Prevent | Define the recovery communication process and approve a spokesperson | Process |  |  | Medium